## Tasks
Resource Adequacy Work Plan for 2010-11 |  | 2010-09-23
TASKS |  | Lead | Status
Assessing Resources
| Develop temperature correlated wind data | Koehler (BPA) | Late 2010?
| Define energy and capacity values for wind | Koehler (BPA) | Ongoing (PNUCC Big Wind, BPA Critical Wind, WECC)
| Update regional hydro sustained peaking capabilty | Fazio (NWPCC) | Done
| Update existing resources, including IPPs | King (NWPCC) | Done
| Update firm export/import contract data | Byrne (BPA) | Done
| Hydro sustained peak capacity survey | Koehler (BPA) | Done, yet to decide what to do next
| Compare resources to NRF and White Book | Adams (PNUCC) | Done
| Peaking capability of hydro independents | Diffely (BPA) | Done
| Define monthly contingency resource | Diffely (BPA) | Preliminary done
| Update out-of-region supply | Diffely (BPA) | Preliminary done
Assessing Load
| Establish definition for normal weather load | Jourabchi (NWPCC) | Unknown
| Update load forecast | Jourabchi (NWPCC) | Done
| Define how conservation is counted | Jourabchi (NWPCC) | Done for regional studies
| Compare loads to NRF and White Book | Adams (PNUCC) | Done
| Define reserve margins | Popoff (PSE) | Done, see PNUCC white paper
| Incorporate balancing reserves (Trapezoidal Model) | Birgit (BPA) | Done
Model Validation and Improvement
| Benchmark Genesys (historic vs. simulated) | Fazio (NWPCC) | Ongoing
| Review Genesys dispatch logic | Fazio (NWPCC) | Ongoing
| Explore use of the PRSI hourly hydro model for the NW | Fazio (NWPCC) | Ongoing (may need more funds for 2011)
| Update Visual Basic interface | BPA | Early 2011
Review Definition of Adequacy
| PSRI report | Fazio (NWPCC) | October 2010
| Single or multiple metrics (i.e. summer/winter, energy/cap)? | Fazio (NWPCC) | Nov-Mar 2011
| Should deterministic metrics be used? | Fazio (NWPCC) | Nov-Mar 2011
| Review of all resource and load assumptions | Diffely (BPA) | Nov-Mar 2011
| Techncical committee review and recommendation | Fazio (NWPCC) | April 2011
| Steering committee recommendation | Fazio (NWPCC) | June 2011
| Council decision to revise standard | Fazio (NWPCC) | August 2011
| Methods to incorporate standard into long-term planning | Various | Ongoing
Integration with Utilities, WECC and NERC
| NERC Workshop | Fazio (NWPCC) | April 27, 28 2010
| LOLP Workshop | Fazio (NWPCC) | Unscheduled
| Develop adequacy framework for utilities | Adams (PNUCC) | Unknown
| Participation in WECC committees | Various | Ongoing
| Revised implementation plan | Gibson (NWPCC) | Waiting for revised standard
Topics for the Steering Committee
Deterministic capacity and energy values for wind
Amount of IPP generation to count on
Amount of out-of-region supply to count on
Amount of contingency resource to count on
Amount of provisional hydro to count on
How to deal with potential F&W impacts
What planned resources to count (i.e. conservation and RPS)
MILESTONES
| Forum's Adequacy Assessment for 2015 |  | November 2010
| Presentation to Council |  | December 2010
| Forum proposed revision to standard |  | June 2011
| Council decision to adopt new standard |  | August 2011
| Assessment for 2016 |  | September 2011
| New Production Version of GENESYS |  | October 2011
| Assessment for 2017 |  | June 2012