| JUDI DANIELSON CHAIR Idaho Jim Kempton Idaho | NORTHWEST POWER PLANNING COUNCIL 851 S.W. SIXTH AVENUE, SUITE 1100 PORTLAND, OREGON 97204-1348 |  |  | TOM KARIER VICE-CHAIR Washington Frank L. Cassidy Jr. "Larry" Washington |
| --- | --- | --- | --- | --- |
| Gene Derfler Oregon Melinda S. Eden Oregon | Fax: 503-820-2370 | Phone: 503-222-5161 1-800-452-5161 | Internet: www.nwcouncil.org | Ed Bartlett Montana John Hines Montana |

June 4, 2003

MEMORANDUM

TO:	Council Members

FROM:	Patty O’Toole

SUBJECT:	REVISED (June 6, 2003) 2003 Accrual Budget - project funding adjustment recommendation and general 2003 budget issues

Action

Following the February submission of recommendations for 2003 accrual based project budgets to Bonneville, the staff has continued to meet with Bonneville and Columbia Basin Fish and Wildlife Authority (CBFWA) staff to discuss the impacts of these recommendations.  A Program Status meeting was held on May 22, 2003 to discuss the following project budget adjustments.

Council staff will present this request to the Fish and Wildlife Committee and the Council during the June 2003 meeting.

Recommendation

The staff recommends that the following budget adjustments, totaling $4,432,210 be approved and that Bonneville be informed of these Council recommendations accordingly.

Background

In December 2002, the Council agreed to help the Bonneville reduce or defer its fish and wildlife spending in 2003 in response to the agency’s financial crisis.  The Council employed the dual objectives of containing costs within $130 million and maintaining support for the project work it approved in past provincial review decisions. This was achieved by establishing a 2003 accrual based budget plan, based on project accrual estimates that totaled $139 million.   This Fiscal Year Accrual Budget Estimate by Project and Contract Report was submitted to Bonneville by the Council on February 21, 2003.  In developing this plan, Council staff, Bonneville and CBFWA agreed that a project spending tracking system and a reallocation system were needed to evaluate projects that are likely not to accrue their planned budget amounts and make these funds available to projects that were severely impacted by the 2003 decisions and need additional funds.

Analysis

Working with Bonneville and CBFWA staff, the Council staff, using the budgets established in the February submission, requests from Bonneville for adjustments, and newly developed budget worksheets from Bonneville, has identified many projects for adjustment at the June Council meeting.  Staff has organized the projects in several categories for discussion purposes.

Categories of projects for consideration of budget adjustments:

1.  FY 2002 accrual (spending limit) impact to 2003 (increases).   $7,683,909

This category of project is by far the largest.  Examples of how FY 2002 may have impacted FY 2003 include projects where the end-of-year accruals estimates were inaccurate or not completed, work was delayed in 2002 until 2003, bills came in late from subcontractors, or bills from sponsors were late in getting to Bonneville. In particular, invoices from federal agencies are often submitted to Bonneville as late as one year after the work occurs.  This situation has not been an issue in past years when carry-over was allowed.

2.  FY 2003 contracted amount different than Council spending limit (increases or reductions).  $238,535

For these projects, Bonneville has issued contracts with a different spending limit from the Council’s accrual estimate.  In some instances, objectives and tasks have been transferred between contracts or projects by Bonneville COTRs.  Realignment of funds associated with these objectives and tasks are necessary.  These have proven to be difficult to track (but the staff doesn’t see reasons for Council objection) and Council staff recommends that Council take formal action on this group of projects for the record.

3.  FY 2003 accrual correction (reduction).  ($3,655,799).

Projects in this category are those where Bonneville has estimated a lower accrual estimate than the Councils estimate, and has provided justification.  Staff has not yet been able to confirm with all project sponsors that they are in agreement with the reductions. Staff recommends adopting these adjustments only if project sponsors agree that the adjustment is appropriate.

4.  Within year reallocation/scope change (increase).  $54,529.

These are projects where either a change in scope has been identified with and increase in funding requested or where an increase is requested in order to meet the existing scope of work.  Staff recommends only approving requests that stay within the original provincial allocated budget.

5.  Capital.  $1,086,460

There are five projects in this category that we propose to change the capital designation (4 from capital to expense, and 1 from expense to capital).

6.  Close outs.  $90,926.

There are five projects in this category that have accrued actual costs and are designated for closure.

7.  Other. $701,038.

This category includes three projects that are considered BiOp critical, and Bonneville estimates a larger accrual from the Council’s February table.

8.  Phase 3.  $1,767,388

Phase 3 includes projects that were originally recommended by the Council for funding during the provincial review but implementation has been deferred due to the 2003 fiscal crisis.

Net adjustment increase of categories 1 - 8:  $4,130,627

General FY 2003 budget information

The FY 2003 was developed using several placeholders.  They are outlined below.

2003 Budget placeholders

| Allocated Spending Cap | $116,229,133 |
| --- | --- |
| RM&E Placeholder | $2,742,500 |
| ISAB/ISRP | $900,000 |
| Subbasin Plans | $4,300,000 |
| BPA overhead + project support | $12,000,000 |
| APRE/HGMP | $1,300,000 |
| TOTAL | $138,729,133 |

Budget adjustments proposed today total $4,130,627.  Council staff recommends that Bonneville consider capitalizing projects 199604300 ($1,002,360) and 198331900 ($1,197,098) for a total of $2,742,500.  The remaining placeholder for RM&E is $2,742,500.  Assuming capitalization of the above projects the overall total FY 2003 budget is within the $139 million spending limit.

| $138,729,133 | Total from above table |
| --- | --- |
| $4,432,210 | Adjustments |
| $143,161,343 | Revised total |
| -$2,199,458 | Explore capitalization of 2 projects |
| -$2,742,500 | RM&E placeholder remaining |
| $138,219,385 | TOTAL |

A table provided by Bonneville is attached, showing FY 2003 actual expenditure through the end of May, 2003.

Attachment:  FY 2003 Project budget adjustments table

________________________________________

w:\po\ww\2003\2003 budget reduction\fy 03 adjustments june commitee memo1.doc