## Table_1_Budget Sum_Council
Table 1. Budget Summary
Contractor:
Project Number |  | 2002-04-700
Project Name: NWPCC APRE/Subbasin Planning Integration
Contract Period: |  | December 1, 2004 through December 31, 2005
Prepared by: DJ Warren & Associates Inc.
Date:
|  |  | Labor | [22 empty] | Travel | [6 empty] | Supplies / Equipment/ Printing |  |  |  | Estimated Project Schedule |  |  | Estimated Full Budget |  |  |  | Estimated FY 04 Budget by Task | Estimated FY 05 Budget by Task | Estimated Startup Budget Through January 2005
| Work Element No. | Work Element, Number and Title | Biometrician / Principal | Fisheries Biologist | Habitat Biologist | Hydo / Fisheries | Data Support | Data, Workshop Support | Programming | Programming / Sub | Workshop Facilitation | 0 | 0 | 0 | Senior Project Manager | Project Coord. / IM,MC | Techncial Writing | Techncial Review | Facilitation | 0 | 0 | 0 | 0 | Total Hours | Labor Cost | Air | Auto Rental | Auto Mileage | Lodging | Meals | Misc. | Travel Cost | Printing / Copies / Other | Office Supplies/Equipment | Field/Research Supplies/Equipment | Supplies / Equipment / Printing | Estimated Days | Start | Finish | Labor | Travel | Supplies, Equip, Printing | TOTAL |  |  | Labor | Travel | Supplies, Equip, Printing | TOTAL
|  |  | L. Mobrand | McConnaha | Watson | Malone | Garrow | Other | Greg Blair | Greyweather | John Barr | 0 | 0 | 0 | Warren | Ziji / Squier | Hemming / Other | Smith | Open | 0 | 0 | 0 | 0
| Element 1A | 1A. Project Management and Coordination | 40 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 155 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 700 | 57285 | 1200 | 0 | 3750 | 546 | 258 | 150 | 5904 | 200 | 0 | 0 | 200 | 283 days | Wed 12/1/04 | Fri 12/30/05 | 57285 | 5904 | 200 | 63389 |  |  | 7720 | 905.5 | 50 | 8675.5
| Element 1B | 1B. NOAA / Coordination / Integration | 140 | 20 | 0 | 20 | 40 | 0 | 20 | 30 | 0 | 0 | 0 | 0 | 30 | 10 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 360 | 39790 | 800 | 0 | 375 | 372 | 152 | 56 | 1755 | 100 | 0 | 0 | 100 | 283 days | Wed 12/1/04 | Fri 12/30/05 | 39790 | 1755 | 100 | 41645 |  |  | 5990 | 532.5 | 50 | 6572.5
| Element 1C | 1C. Set-up and Utilize Steering Committee (Key Entities) | 82 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 25 | 0 | 30 | 10 | 0 | 0 | 0 | 0 | 217 | 23485 | 1600 | 520 | 1875 | 728 | 152 | 200 | 5075 | 250 | 0 | 0 | 250 | 283 days | Wed 12/1/04 | Fri 12/30/05 | 23485 | 5075 | 250 | 28810 |  |  | 3325 | 531.5 | 50 | 3906.5
| Element 1D | 1D. Develop Alternatives for Incorporation into FW Program | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 10025 | 200 | 65 | 187.5 | 95 | 38 | 15 | 600.5 | 50 | 0 | 0 | 50 | 283 days | Wed 12/1/04 | Fri 12/30/05 | 10025 | 600.5 | 50 | 10675.5 |  |  | 900 | 37.5 | 0 | 937.5
| Element 1E | 1E. Provide Formal Reports on Planning Results | 80 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 40 | 90 | 30 | 15 | 0 | 0 | 0 | 0 | 300 | 29110 | 200 | 0 | 112.5 | 95 | 38 | 20 | 465.5 | 100 | 0 | 0 | 100 | 260 days | Mon 1/3/05 | Fri 12/30/05 | 29110 | 465.5 | 100 | 29675.5 |  |  | 0 | 0 | 0 | 0
| Element 2A | 2A. Refine all needs for Implementation | 125 | 10 | 3 | 3 | 80 | 0 | 30 | 60 | 30 | 0 | 0 | 0 | 110 | 80 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 536 | 51484 | 800 | 260 | 750 | 364 | 172 | 100 | 2446 | 100 | 100 | 0 | 200 | 64 days | Wed 12/1/04 | Mon 2/28/05 | 51484 | 2446 | 200 | 54130 |  |  | 10390 | 611.5 | 100 | 11101.5
| Element 2B | 2B. Guidelines / Standards for Process / Methods | 60 | 0 | 0 | 0 | 50 | 0 | 5 | 5 | 30 | 0 | 0 | 0 | 9 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 168 | 16135 | 200 | 65 | 112.5 | 95 | 43 | 20 | 535.5 | 150 | 0 | 0 | 150 | 283 days | Wed 12/1/04 | Fri 12/30/05 | 16135 | 535.5 | 150 | 16820.5 |  |  | 2446 | 56.25 | 50 | 2552.25
| Element 2C | 2C. Data and Information System Design, Development, Support | 305 | 100 | 90 | 135 | 545 | 0 | 564 | 585 | 0 | 0 | 0 | 0 | 22 | 20 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 2441 | 242635 | 1000 | 275 | 562.5 | 315 | 215 | 250 | 2617.5 | 150 | 0 | 0 | 150 | 152 days | Wed 12/1/04 | Thu 6/30/05 | 242635 | 2617.5 | 150 | 245402.5 |  |  | 23467 | 598.5 | 50 | 24115.5
| Element 2D | 2D. Initiate Regional (Province / Basin) Level Workshop (discussions) | 85 | 5 | 5 | 5 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 100 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 505 | 43440 | 2400 | 390 | 740 | 756 | 516 | 180 | 4982 | 200 | 0 | 0 | 200 | 238 days | Mon 1/3/05 | Wed 11/30/05 | 43440 | 4982 | 200 | 48622 |  |  | 6560 | 957 | 50 | 7567
| Element 2E | 2E. Initiate Subasin Level Process to Develop Regional Goals | 457 | 147 | 32 | 165 | 1060 | 0 | 350 | 150 | 267 | 0 | 0 | 0 | 260 | 322 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 3335 | 298734 | 4800 | 1040 | 5437.5 | 3860 | 1672 | 440 | 17249.5 | 1500 | 0 | 4200 | 5700 | 105 days | Tue 2/1/05 | Mon 6/27/05 | 298734 | 17249.5 | 5700 | 321683.5 |  |  | 3008 | 0 | 0 | 3008
| Element 2F | 2F. Conduct Other Associated Follow-up Review | 110 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 75 | 25 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 360 | 34540 | 800 | 260 | 562.5 | 380 | 164 | 60 | 2226.5 | 200 | 0 | 0 | 200 | 283 days | Wed 12/1/04 | Fri 12/30/05 | 34540 | 2226.5 | 200 | 36966.5 |  |  | 0 | 0 | 0 | 0
| Element | Open | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
|  | Total Hours | 1529 | 307 | 130 | 338 | 2055 | 0 | 969 | 830 | 357 | 0 | 0 | 0 | 1181 | 789 | 100 | 402 | 25 | 0 | 0 | 0 | 0 | 9012
|  |  | 214060 | 41138 | 13390 | 43940 | 110970 | 0 | 106590 | 83000 | 30345 | 0 | 0 | 0 | 100385 | 59175 | 7000 | 34170 | 2500 | 0 | 0 | 0 | 0 | 846663 | 846663 | 14000 | 2875 | 14465 | 7606 | 3420 | 1491 | 43857 | 3000 | 100 | 4200 | 7300 |  |  | TOTAL | 846663 | 43857 | 7300 | 897820 | 0 | 0 | 63806 | 4230.25 | 400 | 68436.25
|  | Notes and Assumptions; Budget is at a conceptual stage to be refined during planning | [23 empty] | Air | Auto Rental | Auto Mileage | Lodging | Meals | Misc. | Travel Cost | Printing / Copies / Other | Office Supplies/Equipment | Field/Research Supplies/Equipment | Supplies / Equipment / Printing
|  |  | Title |  | Name |  | Rate / Hour | [24 empty] | 0 |  |  |  | 0 | [8 empty] | Allocation Check
|  |  | Biometrician / Principal |  |  |  | 140 | [24 empty] | 0 |  |  |  | 0
|  |  | Fisheries Biologist |  |  |  | 134 | [14 empty] | 203230 |  | 437773.2 | [7 empty] | 0 |  |  |  | 0
|  |  | Habitat Biologist |  |  |  | 103 | [24 empty] | 0 |  |  |  | 0
|  |  | Hydo / Fisheries |  |  |  | 130 | [24 empty] | 0 |  |  |  | 0
|  |  | Data Support |  |  |  | 54 | [24 empty] | 0 |  |  |  | 0
|  |  | Data, Workshop Support |  |  |  | 75 | [24 empty] | 0 |  |  |  | 0
|  |  | Programming |  |  |  | 110 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Programming / Sub |  |  |  | 100
|  |  | Workshop Facilitation |  |  |  | 85
0
0
0
|  |  | Senior Project Manager |  |  |  | 85
|  |  | Project Coord. / IM,MC |  |  |  | 75
|  |  | Techncial Writing |  |  |  | 70
|  |  | Techncial Review |  |  |  | 85
|  |  | Facilitation |  |  |  | 100
0
0
0
0