## Slide 1: Proposed 2014 RTF Work Plan and 3-year Look Back October 21, 2013

## Slide 2: Work Plan Development Process
RTF 2014 work plan Process | Date
Develop draft work plan and present to Operations subcommittee | Friday, September 4, 2013
Incorporate Operations subcommittee feedback and present draft work plan to RTF | Tuesday, September 17, 2013
Solicit comments on draft work plan from RTF members, the public, and Council (Council directs PAC to review) | Wednesday, September 18, 2013
Receive comments on draft work plan from RTF and public | Monday, October 7, 2013
Post comments and proposed final work plan to October RTF agenda | Tuesday, October 8, 2013
Present final proposed work plan to RTF and develop recommendations | Tuesday, October 15, 2013
Call with P4 to inform of work plan status and recommendations before presenting to Council | Monday, October 21, 2013
Send recommendations from RTF to Council (in Council packet) | Tuesday, October 24, 2013
RTF PAC reviews RTF-adopted work plan and sends recommendations to Council | Thursday, October 31, 2013
Present work plan to Council for approval | Tuesday, November 5, 2013

## Slide 3: Proposed 2014 work plan
 | Proposed 2014 |  |  |  |  | 
Category | Contract RFP 2014 | RTF Contract Staff 2014 | Subtotal Funders 2014 | Council In-Kind Contribution 2014 | % of total | 
Existing Measure Review & Updates | $65,500 | $410,000 | $475,500 | $7,500 | 32% | 50%
New Measure Development & Review of Unsolicited Proposals | $65,000 | $140,000 | $205,000 | $3,000 | 14% | 
Standardization of Technical Analysis | $40,000 | $19,000 | $59,000 | $1,100 | 4% | 
Tool Development | $65,000 | $120,000 | $185,000 | $25,000 | 13% | 22%
Research Projects & Data Development | $60,000 | $60,000 | $120,000 | $42,500 | 8% | 
Regional Coordination | $12,500 | $6,000 | $18,500 | $6,000 | 1% | 
Website, Database support, Conservation Tracking | $25,000 | $40,000 | $65,000 | $75,000 | 4% | 28%
RTF Member Support & Administration | $145,000 | $0 | $145,000 | $5,000 | 10% | 
RTF Management | $4,000 | $196,000 | $200,000 | $112,000 | 14% | 
Subtotal New Work | $482,000 | $991,000 | $1,473,000 | $277,100 | 100% | 100%
 | 33% | 67% |  |  |  | 

## Slide 4: Changes in Work Plan from 2013
Similar allocation among categories
Keeping Contract Staff Model
  Bulk of measure review and development done in-house by RTF contract staff
  Staff maintains flexibility to contract out portions of measure updates as necessary (like cost data research)
Contract out 3rd party QA/QC review of RTF staff work products
Several work plan items still contracted out via RFP
  Research projects, tool development, etc.

## Slide 5: 3-Year Look Back
PAC secured 3-year funding agreement for 2012-2014
RTF developed work plan and business plan each year allocating funding among categories
  Technical Analysis
  Tool Development, Research, Regional Coordination
  Administration
Business model changed in 2013 to bring more contract staff in-house instead of contract RFP

## Slide 6: General Category Comparison
Chart: 
| Technical Analysis | Tool Development, Research, Regional Coordination | Administration
2013 Breakdown | 0.51807 | 0.2226 | 0.25933
Chart: 2012 Breakdown
| Technical Analysis | Tool Development, Research, Regional Coordination | Administration
2012 Breakdown | 0.534 | 0.28 | 0.186
Chart: 
| Technical Analysis | Tool Development, Research, Regional Coordination | Administration
2014 Breakdown | 0.50204 | 0.21962 | 0.27834
Increase in Administration in 2014 due to added website functionality
Reduction in Technical Analysis in 2014 due to less legacy measure review needed

## Slide 7: RTF Budgets – Contract RFP Allocation
Chart: 
| Contract RFP 2012 | Contract RFP 2013 | Contract RFP 2014
RTF Management | 4910 | 2946 | 4000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 25000
Regional Coordination | 0 | 19640 | 12500
Research Projects & Data Development | 176760 | 124714 | 60000
Tool Development | 84452 | 55974 | 65000
Standardization of Technical Analysis | 131588 | 43208 | 40000
New Measure Development & Review of Unsolicited Proposals | 99182 | 90344 | 65000
Existing Measure Review & Updates | 392800 | 118331 | 65500

## Slide 8: RTF Budgets – Contract Staff Allocation
Chart: 
| RTF Contract Staff 2012 | RTF Contract Staff 2013 | RTF Contract Staff 2014
RTF Management | 98200 | 208184 | 196000
RTF Member Support & Administration | 0 | 0 | 0
Website, Database support, Conservation Tracking | 0 | 0 | 40000
Regional Coordination | 56956 | 65794 | 6000
Research Projects & Data Development | 47136 | 24451.8 | 60000
Tool Development | 47136 | 37316 | 120000
Standardization of Technical Analysis | 41244 | 22095 | 19000
New Measure Development & Review of Unsolicited Proposals | 36334 | 67758 | 140000
Existing Measure Review & Updates | 85434 | 421376.2 | 410000

## Slide 9: 2012-2014 RTF Budgets
Chart: 
| Approved 2012 | Approved 2013 | Proposed 2014
RTF Management | 103110 | 211130 | 200000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 65000
Regional Coordination | 56956 | 85434 | 18500
Research Projects & Data Development | 223896 | 149165.8 | 120000
Tool Development | 131588 | 93290 | 185000
Standardization of Technical Analysis | 172832 | 65303 | 59000
New Measure Development & Review of Unsolicited Proposals | 135516 | 158102 | 205000
Existing Measure Review & Updates | 478234 | 539707.2 | 475500

## Slide 10: 2012-2014 RTF Budgets
Chart: 
| Approved 2012 | Approved 2013 | Proposed 2014
RTF Management | 103110 | 211130 | 200000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 65000
Regional Coordination | 56956 | 85434 | 18500
Research Projects & Data Development | 223896 | 149165.8 | 120000
Tool Development | 131588 | 93290 | 185000
Standardization of Technical Analysis | 172832 | 65303 | 59000
New Measure Development & Review of Unsolicited Proposals | 135516 | 158102 | 205000
Existing Measure Review & Updates | 478234 | 539707.2 | 475500
Increase due to new measures being submitted and increased staff review effort

## Slide 11: 2012-2014 RTF Budgets
Chart: 
| Approved 2012 | Approved 2013 | Proposed 2014
RTF Management | 103110 | 211130 | 200000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 65000
Regional Coordination | 56956 | 85434 | 18500
Research Projects & Data Development | 223896 | 149165.8 | 120000
Tool Development | 131588 | 93290 | 185000
Standardization of Technical Analysis | 172832 | 65303 | 59000
New Measure Development & Review of Unsolicited Proposals | 135516 | 158102 | 205000
Existing Measure Review & Updates | 478234 | 539707.2 | 475500
Decrease due to reduction in effort on Guidelines once complete in late 2012

## Slide 12: 2012-2014 RTF Budgets
Chart: 
| Approved 2012 | Approved 2013 | Proposed 2014
RTF Management | 103110 | 211130 | 200000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 65000
Regional Coordination | 56956 | 85434 | 18500
Research Projects & Data Development | 223896 | 149165.8 | 120000
Tool Development | 131588 | 93290 | 185000
Standardization of Technical Analysis | 172832 | 65303 | 59000
New Measure Development & Review of Unsolicited Proposals | 135516 | 158102 | 205000
Existing Measure Review & Updates | 478234 | 539707.2 | 475500
Changes due to increased tool development and efforts to simplify

## Slide 13: 2012-2014 RTF Budgets
Chart: 
| Approved 2012 | Approved 2013 | Proposed 2014
RTF Management | 103110 | 211130 | 200000
RTF Member Support & Administration | 170868 | 170868 | 145000
Website, Database support, Conservation Tracking | 0 | 0 | 65000
Regional Coordination | 56956 | 85434 | 18500
Research Projects & Data Development | 223896 | 149165.8 | 120000
Tool Development | 131588 | 93290 | 185000
Standardization of Technical Analysis | 172832 | 65303 | 59000
New Measure Development & Review of Unsolicited Proposals | 135516 | 158102 | 205000
Existing Measure Review & Updates | 478234 | 539707.2 | 475500
Increase due to hiring RTF manager, website functionality, and more processes to manage

## Slide 14: High Level Staff Observations
Majority of budget on in-house contract staff
  Much improved throughput & depth of analysis
  Significant cost savings in $/output compared to an all-RFP model
Work products using in-house staff have been more consistent, requiring less re-work
  Guidelines have helped greatly with this effort
  Cohesive staff team & intra-staff review adds quality
3rd party QC has added to more complete documentation sourcing and completeness of analysis
  No major flaws have been uncovered in reviews

## Slide 15: High Level Staff Observations
RTF voting members becoming more familiar with Guidelines requirements and meaning of terms
  Staff able to more easily assess workload because of this
Current level of contract staff is likely sufficient for 2014 work
  Future projections show more staff may be needed
More subcommittee work is needed
  Complex work products will likely be reviewed in subcommittee instead of full RTF
  Adds needed level of staff support to facilitate, prepare, and summarize for full RTF
Standardization of processes is improving
  In-house staff has helped increase transparency

## Slide 16: Council Impact
Continual shift of technical & management work to RTF staff
  Reliant on Tom & Charlie for technical & management guidance – but much less analysis & implementation
  In-kind contribution still remains substantial ($275,000) = ~2 FTE Council staff
Heavily rely on Council for:
  IT assistance, database, website development & hosting
  Contracts development
  Accounting
  Administration of meeting space & setup
  Legal (charter, by-laws, contract review)

## Slide 17: Contact
For more information, contact:
  Nicholas O’Neil, P.E.
  Northwest Power and Conservation Council
  851 SW 6th Ave
  Suite 1100
  Portland, OR 97204
  noneil@nwcouncil.org
  503.820.2312