## Strawman Project Plan
% Complete | Task Group | Task # | Task Name | Duration | Start Date | Due Date
100% | Member Recruitment | 1 | Add SAAC members and interested parties to CRM | 9 | 2013-05-16 | 2013-05-24
100% | Member Recruitment | 2 | Draft a description of the purpose of the task force and expected outcome | 5 | 2013-05-20 | 2013-05-24
100% | Member Recruitment | 3 | Email flexibility metric meeting attendees and SAAC members and interested parties soliciting participation | 5 | 2013-06-17 | 2013-06-21
100% | Member Recruitment | 4 | Finalize list of task force members | 5 | 2013-06-24 | 2013-06-28
33% | Initial Tasks | 5 | Determine proposed subject matter / sections for final paper | 21 | 2013-09-10 | 2013-09-30
100% | Initial Tasks | 6 | Prepare Strawman Project Proposal | 10 | 2013-09-10 | 2013-09-19
0% | Initial Tasks | 7 | Meet with task force to set agenda and scope | 1 | 2013-09-24 | 2013-09-24
0% | Initial Tasks | 8 | Revise project plan based on meeting input and resend to FAM Workgroup | 6 | 2013-09-25 | 2013-09-30
0% | Initial Tasks | 9 | Email SAAC when plan is finalized | 1 | 2013-10-07 | 2013-10-07
0% | Draft report tasks | 10 | Write a literature review | 46 | 2013-10-01 | 2013-11-15
0% | Draft report tasks | 11 | Collect references from workgroup | 4 | 2013-10-01 | 2013-10-04
0% | Draft report tasks | 12 | Send reference list to workgroup | 1 | 2013-10-07 | 2013-10-07
0% | Draft report tasks | 13 | Read references | 18 | 2013-10-01 | 2013-10-18
0% | Draft report tasks | 14 | Create a rough draft of a literature review and send to workgroup | 19 | 2013-10-21 | 2013-11-08
0% | Draft report tasks | 15 | Revise rough draft based on feedback | 16 | 2013-11-11 | 2013-11-26
0% | Draft report tasks | 16 | Write a section on current IRP approaches in the Northwest | 46 | 2013-10-01 | 2013-11-15
0% | Draft report tasks | 17 | Collect current IRPs with quantitative flexibility assessments | 4 | 2013-10-01 | 2013-10-04
0% | Draft report tasks | 18 | Send IRPs to workgroup | 1 | 2013-10-07 | 2013-10-07
0% | Draft report tasks | 19 | Read IRPs | 18 | 2013-10-01 | 2013-10-18
0% | Draft report tasks | 20 | Create a rough draft of an IRP review and send to workgroup | 19 | 2013-10-21 | 2013-11-08
0% | Draft report tasks | 21 | Revise rough draft based on feedback | 16 | 2013-11-11 | 2013-11-26
0% | Draft report tasks | 22 | Select methods for qualitative and quantitative comparison | 10 | 2013-11-18 | 2013-11-27
0% | Draft report tasks | 23 | Reread literature review and IRP review | 3 | 2013-11-18 | 2013-11-20
0% | Draft report tasks | 24 | Meet with the workgroup and discuss which methods to review | 7 | 2013-11-21 | 2013-11-27
0% | Draft report tasks | 25 | Determine the number of methods that will be tested against the collected dataset | 7 | 2013-11-21 | 2013-11-27
0% | Draft report tasks | 26 | Have workgroup members rank methods and use ranking to select subset | 7 | 2013-11-21 | 2013-11-27
0% | Draft report tasks | 27 | Identify and collect data that will be used for comparing methods | 58 | 2013-10-01 | 2013-11-27
0% | Draft report tasks | 28 | Email workgroup to solicit input on canidate datasets | 11 | 2013-10-01 | 2013-10-11
0% | Draft report tasks | 29 | Meet with workgroup and discuss merits of datasets | 12 | 2013-10-14 | 2013-10-25
0% | Draft report tasks | 30 | Create or identify database or files containing information for method comparison | 31 | 2013-10-28 | 2013-11-27
0% | Draft report tasks | 31 | Use existing programs or write minimal programs to implement the methods for comparison | 61 | 2013-12-02 | 2014-01-31
0% | Draft report tasks | 32 | Identify existing program and assess capacity to use collected dataset | 45 | 2013-12-02 | 2014-01-15
0% | Draft report tasks | 33 | Write basic programs or models where needed to implement method on collected dataset | 45 | 2013-12-02 | 2014-01-15
0% | Draft report tasks | 34 | Collect output from existing and new models into tables or other summary statistics | 16 | 2014-01-16 | 2014-01-31
0% | Draft report tasks | 35 | Create graphs and other data visualizations from output data | 16 | 2014-01-16 | 2014-01-31
0% | Draft report tasks | 36 | Write conclusions from each method | 12 | 2014-02-03 | 2014-02-14
0% | Draft report tasks | 37 | Create a rough draft of conclusions for each method examined and send to the workgroup | 5 | 2014-02-03 | 2014-02-07
0% | Draft report tasks | 38 | Revise rough drafts based on feedback | 5 | 2014-02-10 | 2014-02-14
0% | Draft report tasks | 39 | Write overall conclusions for the report | 11 | 2014-02-18 | 2014-02-28
0% | Draft report tasks | 40 | Create a rough draft of the overall conclusions and send to workgroup | 4 | 2014-02-18 | 2014-02-21
0% | Draft report tasks | 41 | Revise rough draft of the overall conclusions based on feedback | 5 | 2014-02-24 | 2014-02-28
0% | Draft report tasks | 42 | Send draft report to FAM Workgroup members for any final comments and revisions | 19 | 2014-03-03 | 2014-03-21
0% | Draft report tasks | 43 | Collect all sections into single report | 2 | 2014-03-03 | 2014-03-04
0% | Draft report tasks | 44 | Edit for consistent voice/style | 3 | 2014-03-05 | 2014-03-07
0% | Draft report tasks | 45 | Send draft to workgroup for feedback | 5 | 2014-03-10 | 2014-03-14
0% | Draft report tasks | 46 | Revise based on feedback | 2 | 2014-03-17 | 2014-03-18
0% | Draft report tasks | 47 | Get draft approved for presentation to SAAC by workgroup | 3 | 2014-03-19 | 2014-03-21
0% | Draft report tasks | 48 | Present draft report to SAAC | 5 | 2014-03-24 | 2014-03-28
0% | Draft report tasks | 49 | Revise based on SAAC feedback | 5 | 2014-03-31 | 2014-04-04
0% | Final report tasks | 50 | Publish draft report on website and open 30 day comment period | 32 | 2014-04-07 | 2014-05-08
0% | Final report tasks | 51 | Review comments with FAM Workgroup and revise draft report based on comments or provide responses to comments | 5 | 2014-05-12 | 2014-05-16
0% | Final report tasks | 52 | Present revised draft to SAAC for further comments or revisions | 12 | 2014-05-19 | 2014-05-30
0% | Final report tasks | 53 | Finalize report and post on the SAAC website | 5 | 2014-06-02 | 2014-06-06